## Timeline (hidden)
Updated: 12/11 | Completed | Planned | Deferred | Cancelled
Action | Task | Consultant Days | Council Days | Outcome | Start | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01
Apply for Neighbourhood Area to NYC | Parish Council approval | 0 | 1 | Completed: https://edemocracy.northyorks.gov.uk/ieDecisionDetails.aspx?Id=5011
Inform neighbouring PCs
Inform NY Councillor
Establish Steering Group (PC) | Invite any additional members identified - Carlton Towers - Businesses - School - Cricket Club - Local Groups - Farms | 0 | 1 | Completed: Andrew, Paul, Lisa, Adrian & Geoff | bar: 2024-09-01
| Set up NDP page on PC website | 0 |  | Completed: Helen to add link | bar: 2024-07-01
Apply to Locality for grant | Consultant to support Clerk | 0 | 0.5 | Completed: Awarded: NP Grant Ref: NPG-13924 £4,960.00
First Working Group Meeting | Agree Plan, ToR, Actions | 0 | 1 | Completed: 3/Sept | bar: 2024-09-01
Regular Steering group Meetings |  | 1 | 1 | Planned Month to Month Nov/Jan/Feb | bar: 2024-10-01 to 2025-03-01; 2025-05-01
Visioning Exercise: Steering Group |  | 1 | Consultant early review of surveys, evidence, data | - Committee own views playback (Report - David) - Stakeholder Map (Activity & Report - Andrew) - Event Planning (Ideas - All) - See Brainstorm - Budget Plan (Helen) - Forward Plan meetings and actions (Schedule - Helen) | bar: 2024-09-01 to 2024-11-01
Community Announcement, Invite to Event | Production of promotional/information materials | 1 | 1 | bar: 2024-09-01 to 2025-01-01
| Social Media | 0 | 1 | bar: 2024-09-01 to 2025-01-01
| Postal | 0 | 1 | bar: 2024-09-01 to 2025-02-01
Launch Event/Visioning Exercise: Wider Community | Inform the community. Letters to stakeholders including neighbouring PCs | 2 | 1 | bar: 2024-10-01 to 2025-02-01
Event: - Village hall and materials - School Vision 2045 - Carlton Culture Brainstorming - Do not wants - Village Map | bar: 2024-10-01 to 2025-02-01
Policy Intentions Document (PID) writing | Identify design/print firm - quote | 0 | 1 | bar: 2024-11-01 to 2025-05-01
| Production / Write Document | 2.5 | 3 | bar: 2024-11-01 to 2025-05-01
Policy Intentions Document (PID) consultation (6 weeks) | Community consultation event. PID distributed to all | 0 | 0 | bar: 2024-11-01 to 2025-10-01
PID Evidence | 6 themes | bar: 2024-11-01 to 2025-11-01
WRITING THE PLAN 2024/2025 | Review evidence based Documents | 0.5 | 1 | bar: 2025-01-01 to 2025-12-01
| Review revised Publication draft Selby Local Plan | 0 | 1 | bar: 2025-01-01 to 2025-12-01
| Review outcomes of PID consultation | 0 | 1 | bar: 2025-01-01 to 2025-12-01
| Establish working groups as necessary to gather evidence | 0 | 1 | bar: 2025-01-01 to 2025-12-01
Draft Regulation 14 pre submission Plan | Draft Regulation 14 pre submission consultation document | 4 | 1 |  |  | 2026-01-01: Council Approve Draft Plan; 2026-02-01: Prublication / design
Regulation 14 consultation | bar: 2026-03-01 to 2026-05-01
Modifications to Pre submission Plan | bar: 2026-06-01 to 2026-08-01
Basic Conditions Statement & Consultation Statement | bar: 2026-09-01
Submission to North Yorkshire Council | bar: 2026-09-01
Regulation 16 consultation (NYC) | [5 empty] | 2026-10-01: Pend on NYC
Appointment of Examiner/Examination | bar: 2026-09-01 to 2027-03-01
Referendum | bar: 2027-04-01
Making of Plan – ‘adoption’ | bar: 2027-04-01 to 2027-05-01

## Tasks - Alloted & Completed
Action | Task Alloted to.. | Completed Date | Notes
Completed
Contact Natalie Land Re: Best Village Hall Committee Rep | Helen Phillips | 2024-11-14 | Contacted Malcolm Hancock by email- agreed to attend on 8/1/25
Contact Abby Proctor- Youth Club/ Pollington FA | Helen Phillips | 2024-11-14 | Contacted Abby by email - agreed to attend on 8/1/25
Re-issue the 'Explaining the NDP document to all Cllrs | Helen Phillips | 2024-11-13 | Sent by email
Re-issue the Ourplace survey link to all Cllrs | Helen Phillips | 2024-11-13 | Sent by email
Add agenda topic of 'Carlton Holy Family School Future' for PC meeting 26/11/24 | Helen Phillips | 2024-11-14 | completed
Inform Snaith Town Council about intention to raise NDP | Helen Phillips | 2024-11-13 | completed
Get dates/bookings availability for Community Event in Feb 2025 | Helen Phillips/ Andrew Palmer | 2024-11-14 | Booked the Village Hall for 23rd February 2025 for the 'Event Day' 1-4pm
Populate the Council's website NDP page further | Helen Phillips/ Adrian Lowes/ Andrew Palmer | Completed | (added introduction 15/11/24 HP)
Contact Jon Watson/ Katherine Pierce - Carlton Primary School | Andrew Palmer | 2024-12-04 | Jon Watson ok to join
Add a colour key to the Timeline Log | Andrew Palmer | 2024-11-14 | done
What is Neighbouthood Plan on a Page | Andrew Palmer | Completed | completed
Issue info for Assets of Community Value | David Gluck | 2024-11-14 | Sent by email
To provide counter clicker, map pins, pens and post-its | Helen P | 2025-01-09 | received 10-01-25
Actions to Finalise
Contact Hardeep Singh - Londis Store | Andrew Palmer | Business & Commerce | Contacted but Hardeep is emailing back - Awaiting update
Contact Keeley from Frying Nemo | Adrian Lowes | Business & Commerce | Contacted, awaiting response
Contact WI/ Margaret Clayton | Adrian Lowes | Herritage | Contacted, willing to join
Contact Lisa/ The Forresters | Lisa Quinn | Business & Commerce | Contacted, awaiting response
Email Allocated Planning Officer - Helen Gregory -to introduce WG | Andrew Palmer | Completed | David Gluck has made contact with Helen Gregory
Provide timesheet data for the WG | David Gluck | Completed | received 11-01-25
Raise a Community Facebook page for NDP Info | Adrian Lowes/ Andrew Palmer | Completed
Include info in noticeboards | Helen Phillips | Completed
Price for printing of flyers | Helen Phillips | 2025-02-23 | completed at a cost of £88.00
Businesses flyer adding | Abby Proctor | 2025-02-23 | Completed
Insertion of event flyer in School newsletter | Andrew Palmer/ Jon Watson | w/c 13/01/25 ideally | Completed
Draft event flyer production | Abby Proctor | w/c 13/01/25 ideally | Completed and printed
Approach CO-OP re: refreshments for 'event' depending on venue | Lisa Quinn | 2025-02-13
To provide large pinable map | David Gluck | 2025-02-23
To man the 'explanation' comparison (Carlton v NYC Plan) station at the event | David Gluck | 2025-02-23
Our-Place results wheel graph | David Gluck/ Paul | 2025-02-23
Our-Place station manning (with laptop) | Abby Proctor/ Paul | 2025-02-23
Laptop for Our-Place station | David Gluck | 2025-02-23
Survery Station manning | Andrew Palmer | 2025-02-23
Tea/ Coffee/ Refreshments & bar facility | Carlton Village Hall Committee - Natalie Land | 2025-02-23
A' frames and Board supply | David Gluck | 2025-02-23
Liaison with Mike Jordan's distribution team for flyer delivery | Helen Phillips | for delivery w/c 17/02/25 | Completed; Andrew to contact further
Childrens Wants Competition | Andrew Palmer | 2025-02-23
Provision of Amazon voucher for Competition prizes | Helen Phillips | 2025-02-23
Contact York Mix Radio | Adrian Lowes | 2025-02-23 | ?
Social Media insertions | Abby/ Adrian/ Andrew | 2025-02-23
Arrangement of attendance of a Parish member of an already in situ NDP | David Gluck | 2025-02-23
Update Timeline Log after meetings | Andrew Palmer | on-going
Provision of feedback and analysis of data gathered from event | Andrew Palmer & David Gluck | Completed 11/03/25
To complete the end report for the initial funding application | Helen Phillips | 2025-03-19
To Complete
To add the event analysis data to website and noticeboards | Helen Phillips
Policy Intnetion Document | David Gluck |  | Drafted 14th May
Reach out to Carlton Towers | Helen Phillips | 2025-09-12 | Sent PID
Share Online Tool with Social Media - Our Space | David / Andrew
Sub Groups to Look at Policy Proposals | TBC |  | To Be Planned at Meeting 24th Sept
Sub Group Templates | David Gluck
Sub Group public consultations / collect evidence | TBC
Photos of Carlton through the year Competition | Lisa Quinn
ACON Design Code (?) | Helen / David
Gather and collate photographs of the village for future use in the Plan | Lisa Quinn
PID on Website | Helen Phillips
PID Feedback Surbey and Costs | David Gluck
Points of Interest in Village - Tour? | David Gluck

## Timeline Sept25
Updated: 12/11 | Completed | Planned | Deferred | Cancelled
Action | Task | Consultant Days | Council Days | Outcome | Start | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01
Apply for Neighbourhood Area to NYC | Parish Council approval | 0 | 1 | Completed: https://edemocracy.northyorks.gov.uk/ieDecisionDetails.aspx?Id=5011
Inform neighbouring PCs
Inform NY Councillor
Establish Steering Group (PC) | Invite any additional members identified - Carlton Towers - Businesses - School - Cricket Club - Local Groups - Farms | 0 | 1 | Completed: Andrew, Paul, Lisa, Adrian & Geoff | bar: 2024-09-01
| Set up NDP page on PC website | 0 |  | Completed: Helen to add link | bar: 2024-07-01
Apply to Locality for grant | Consultant to support Clerk | 0 | 0.5 | Completed: Awarded: NP Grant Ref: NPG-13924 £4,960.00
First Working Group Meeting | Agree Plan, ToR, Actions | 0 | 1 | Completed: 3/Sept | bar: 2024-09-01
Regular Steering group Meetings |  | 1 | 1 | Planned Month to Month Nov/Jan/Feb | bar: 2024-10-01 to 2025-03-01; 2025-05-01
Visioning Exercise: Steering Group |  | 1 | Consultant early review of surveys, evidence, data | - Committee own views playback (Report - David) - Stakeholder Map (Activity & Report - Andrew) - Event Planning (Ideas - All) - See Brainstorm - Budget Plan (Helen) - Forward Plan meetings and actions (Schedule - Helen) | bar: 2024-09-01 to 2024-11-01
Community Announcement, Invite to Event | Production of promotional/information materials | 1 | 1 | bar: 2024-09-01 to 2025-01-01
| Social Media | 0 | 1 | bar: 2024-09-01 to 2025-01-01
| Postal | 0 | 1 | bar: 2024-09-01 to 2025-02-01
Launch Event/Visioning Exercise: Wider Community | Inform the community. Letters to stakeholders including neighbouring PCs | 2 | 1 | bar: 2024-10-01 to 2025-02-01
Event: - Village hall and materials - School Vision 2045 - Carlton Culture Brainstorming - Do not wants - Village Map | bar: 2024-10-01 to 2025-02-01
Policy Intentions Document (PID) writing | Identify design/print firm - quote | 0 | 1 | bar: 2024-11-01 to 2025-05-01
| Production / Write Document | 2.5 | 3 | bar: 2024-11-01 to 2025-05-01
Policy Intentions Document (PID) consultation (6 weeks) | Community consultation event. PID distributed to all | 0 | 0 |  |  | 2025-06-01: Locality Funding Removed - Replanning; 2025-10-01: P
PID Evidence | 6 themes | bar: 2025-10-01 to 2025-11-01
WRITING THE PLAN 2024/2025 | Review evidence based Documents | 0.5 | 1 | bar: 2025-11-01 to 2025-12-01
| Review revised Publication draft Selby Local Plan | 0 | 1 | bar: 2025-11-01 to 2025-12-01
| Review outcomes of PID consultation | 0 | 1 | bar: 2025-11-01 to 2025-12-01
| Establish working groups as necessary to gather evidence | 0 | 1 | bar: 2025-11-01 to 2025-12-01
Draft Regulation 14 pre submission Plan | Draft Regulation 14 pre submission consultation document | 4 | 1 |  |  | 2026-01-01: Council Approve Draft Plan; 2026-02-01: Prublication / design
Regulation 14 consultation | bar: 2026-03-01 to 2026-05-01
Modifications to Pre submission Plan | bar: 2026-06-01 to 2026-08-01
Basic Conditions Statement & Consultation Statement | bar: 2026-09-01
Submission to North Yorkshire Council | bar: 2026-09-01
Regulation 16 consultation (NYC) | [5 empty] | 2026-09-01: Dependency on NYC
Appointment of Examiner/Examination | [5 empty] | 2026-09-01: Dependency on NYC
Referendum | bar: 2027-04-01
Making of Plan – ‘adoption’ | bar: 2027-04-01 to 2027-05-01

## Brainstorming Lists
Brainstorming Lists
Meeting date | Topic | List
2024-11-12 | Village Community Involvement | Hardeep Singh - Londis (Andrew)
Abby Proctor - Youth Group (Helen)
Lisa Benson - Forresters (Lisa)
Margaret Clayton - WI (Adrian)
Keely Richardson - Frying Nemo (Adrian)
Jon Watson - Primary School (Andrew)
Sharon Hancock - Village Hall (Helen)
Mike Jordan - NYC
Odddfellows
Doctor's Surgery
BATA Store
North Yorkshire Youth Group
Maed in Ink
Annie Newbold - NY Police
Jane Pemberton - Friends of Carlton
Neil Broadhead - Auto Garage
Isabelle - Snatih Against Loss
Stephen Cass - Cricket Club
Lynda Partington - Carlton Playgroup
Lesley Streets - Allotments
Sheena Grice
Mark Bailey - Madam Gilbert School
Methodist Church
Samantah Law - Brownies and Rainbows
Laura Sheers - Sandwich Shop
Louise - The Workshop
Richard Everett
Helen Snowden
Margaret Kilner - Catholic Church
Enid Brown - Parochial Church
Christine Knot - Black Dog Brewery
Sam Coverdale-Waterhouse - Carlton Towers
Alice - I.Lounge
Ruth Ainling - Read School
David Leek - New Coates Hall Farm
Paul Cooper Family
Carl - Art Club
Shaun Marshall - Field Owner
2024-11-12 | Community Activities | NoticeBoards (Helen)
1st Village Hall Event Feb (Helen / Andrew)
PC Website (Adrian / Helen / Andrew)
Community Facebook Page (Adrian / Lisa / Andrew)
Facebook Survey
Door to Door Canvassing
Victoria & David Local Radio
Youth group activities
Pub Quiz
Local Brand Activity
Mailshot questionaire
Leaflets to community groups
Newsletter
Leaflet drop
Selby Times
Event in Village
School Competition
Stalls at Fairs
School & College logo competition
Community Survey Paper & Online
Photo Competition